## Product Backlog
ID | User Story | Module | Acceptance Criteria | Planned Week | Status
US1 | As a traffic operator, I want the system to detect vehicle number plates so that I can identify vehicles automatically. | ANPR Detection | System detects number plates for >95% of clear daylight vehicles in test video. | Week 1 | Done
US2 | As a traffic operator, I want OCR to extract text from detected plates so that I can store registration numbers in the database. | OCR Number Plate Recognition | OCR correctly reads at least 90% of clear plate numbers. | Week 2 | Done
US3 | As an authority, I want the system to calculate vehicle speed so that I can detect over-speeding vehicles. | Speed Violation Detection | System logs a violation when speed exceeds configurable limit. | Week 3 | In Progress
US4 | As an analyst, I want the system to count vehicles so that daily traffic flow can be measured. | Vehicle Counting | Total count matches manual count within 5% error. | Week 3 | In Progress
US5 | As an analyst, I want vehicles to be classified as car/bike/truck so that category-wise reports can be generated. | Vehicle Classification | Classification accuracy above 85% on test dataset. | Week 4 | Planned
US6 | As a planner, I want to measure traffic density so that peak congestion periods can be identified. | Traffic Density Measurement | System labels density correctly for sample low/medium/high videos. | Week 4 | Planned
US7 | As an operator, I want a live dashboard so that I can see counts and violations in real time. | Live Dashboard & Analytics | Dashboard refreshes within a few seconds and shows latest counts. | Week 5 | Planned
US8 | As an administrator, I want all data stored in a database so that historical analytics and reports can be generated. | Database Storage & Reports | All events (vehicles, violations) are stored and retrievable by date/time filters. | Week 6 | Planned
US9 | As an operator, I want basic reports for a given day so that I can submit them to higher authorities. | Database Storage & Reports | System exports daily report with counts and violations in tabular format. | Week 7 | Planned