## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rohit | 21-11-2025 | OCR accuracy is low for night-time plates with glare | Sprint 4 | Rohit | Functional | Tune OCR preprocessing (grayscale, thresholding) and retrain model on night dataset |  | Open | High priority
2 | Rohit | 21-11-2025 | Fast moving vehicles sometimes not detected by ANPR | Sprint 3 | Rohit | Functional | Increase camera FPS and adjust detection region + tracking thresholds |  | Open | Needs re-testing after fix
3 | Rohit | 21-11-2025 | Misclassification between car and mini-truck in ATCC module | Sprint 5 | Rohit | Classification | Collect more labelled samples and fine-tune ATCC model |  | Open | Medium priority
4 | Rohit | 21-11-2025 | Dashboard vehicle counts occasionally lag behind real-time feed | Sprint 6 | Rohit | Performance | Optimize DB queries and reduce dashboard refresh interval |  | Open | Monitor after optimization
5 | Rohit | 21-11-2025 | Database insert time increases when records exceed 100k | Sprint 6 | Rohit | Performance | Add proper indexing and consider archiving old records |  | Open | Plan optimization in next release
6 | Rohit | 21-11-2025 | Dashboard layout not responsive on small laptop screens | Sprint 2 | Rohit | UI/UX | Apply responsive CSS/Bootstrap grid and test on 1366x768 resolution |  | Open | Cosmetic but visible

## Sheet2
Logical
User Interface
Maintainability
Standards
Others